## 1. User Roles & Permissions
Module / Feature Area | Specific Capability / Action | Super Admin | Org Admin | Product Mgr / Member | Compliance Officer | External Supplier | Public / Consumer
Authentication & Profile | Sign in / Sign out / Password Reset | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Magic Link | ❌ No Login
Authentication & Profile | Manage Personal Profile & API Keys | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Tenant & Org Management | Create New Organizations / Tenants | ✅ Yes | ❌ No | ❌ No | ❌ No | ❌ No | ❌ No
Tenant & Org Management | Edit Company Details & Branding | ✅ Yes | ✅ Yes (Own Org) | ❌ View Only | ❌ View Only | ❌ No | ❌ No
User & Access Governance | Invite & Manage Team Members | ✅ Cross-Org | ✅ Yes (Own Org) | ❌ No | ❌ No | ❌ No | ❌ No
User & Access Governance | Assign & Revoke User Roles | ✅ Yes | ✅ Yes (Non-Admin) | ❌ No | ❌ No | ❌ No | ❌ No
Supply Chain Directory | Add "From" Suppliers & "To" Clients | ✅ Yes | ✅ Yes | ✅ Yes | ❌ View Only | ❌ No | ❌ No
Supply Chain Directory | Request Material Compliance from Supplier | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Supply Chain Directory | Submit Tier-2 Material Declarations | ❌ No | ❌ No | ❌ No | ❌ No | ✅ Yes (Own Part) | ❌ No
Product Master Catalog | Create / Edit Product Models & SKUs | ✅ Yes | ✅ Yes | ✅ Yes | ❌ View Only | ❌ No | ❌ No
Product Master Catalog | Bulk Upload SKUs via CSV / Excel | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
DPP Passport Engine | Create Draft Passport (Wizard) | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No
DPP Passport Engine | Edit Technical & Material Fields | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No
DPP Passport Engine | Approve & Formally Publish Passport | ✅ Yes | ✅ Yes | ❌ Request Only | ✅ Yes | ❌ No | ❌ No
DPP Passport Engine | Archive / Revoke Passport | ✅ Yes | ✅ Yes | ❌ No | ✅ Yes | ❌ No | ❌ No
GS1 QR Code Manager | Generate & Download Vector SVG/PNG QR | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ Scan Only
Dynamic QR Scan View | View Public Sustainability & Care Data | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Dynamic QR Scan View | View Professional Disassembly & Repair | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ Restricted | ❌ No
Dynamic QR Scan View | View Authority Test Certs (eIDAS) | ✅ Yes | ✅ Yes | ❌ Restricted | ✅ Yes | ❌ No | ❌ No
Audit Trail & Compliance | View 10-Year Immutable Changelog | ✅ Yes | ✅ Yes | ❌ View Recent | ✅ Full History | ❌ No | ❌ No
Export & Interoperability | Download JSON-LD & PDF Certificate | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No

## 2. Screen & Button Blueprint
Page / Screen Name | Route / URL | UI Section / Card | Element / Button / Field Name | Element Type | Functional Description & Action | User Feedback / Output | Allowed Roles
Sign In / Login | /login | Main Form | Email Input | Text Input | User enters registered corporate email address | Inline validation if invalid format | All Registered
Sign In / Login | /login | Main Form | Password Input | Password Input | User enters password with hide/show toggle button | Masked characters, eye toggle | All Registered
Sign In / Login | /login | Main Form | Sign In Button | Primary Button | Submits credentials to /api/auth/login, receives JWT tokens | Loading spinner -> Redirects to Dashboard | All Registered
Sign In / Login | /login | Footer | Forgot Password Link | Text Link | Triggers password reset email workflow | Opens reset modal with success toast | All Registered
Operations Hub | /dashboard | Top Metric Strip | Total Passports Badge | Metric Card | Displays total passports count and active vs draft breakdown | Click filters table to active passports | Super Admin, Org Admin, Member, Compliance
Operations Hub | /dashboard | Top Metric Strip | Compliance Health Index | Metric Card | Displays overall regulatory compliance percentage (e.g. 96%) | Color coded (Green >90%, Amber 70-90%) | Super Admin, Org Admin, Member, Compliance
Operations Hub | /dashboard | Top Metric Strip | Active QR Scans Gauge | Metric Card | Displays consumer & professional scan count in last 30 days | Live scan counter with trend arrow | Super Admin, Org Admin, Member, Compliance
Operations Hub | /dashboard | Category Filter | Vertical Tabs (All/Textiles/Batteries/Tech) | Tab Selector | Filters dashboard analytics and list by industry vertical | Refreshes metrics & tables instantaneously | All Authenticated
Operations Hub | /dashboard | Action Bar | + Create Passport Button | Primary Button | Navigates user directly to /dpp-wizard | Opens step 1 of DPP Wizard | Super Admin, Org Admin, Member, Compliance
Operations Hub | /dashboard | Action Bar | Export Report Button | Secondary Button | Exports dashboard summary into PDF/Excel format | Downloads summary report file | Super Admin, Org Admin, Compliance
Operations Hub | /dashboard | Passports Table | Passport Row Actions (View/Edit/QR) | Action Group | Quick links to view details, resume draft, or download QR | Opens relevant drawer/page | Role-dependent
Supply Chain Directory | /company-management | Partner Filter Tabs | All / Suppliers ("From") / Clients ("To") / Recyclers | Tab Selector | Segments supply chain partners by provenance role | Filters partner grid in real time | All Authenticated
Supply Chain Directory | /company-management | Search & Action Bar | Search Partner Input | Search Input | Filters partners by legal name, country, or EORI number | Instant client-side / server debounce filter | All Authenticated
Supply Chain Directory | /company-management | Search & Action Bar | + Add Partner Button | Primary Button | Opens slide-over drawer to register new supplier or OEM | Opens Add Partner Drawer | Super Admin, Org Admin, Member
Supply Chain Directory | /company-management | Add Partner Drawer | Partner Role Selector | Dropdown Select | Specifies role: Tier-1 Supplier, Tier-2 Supplier, Client OEM, Recycler | Adapts required due-diligence fields | Super Admin, Org Admin, Member
Supply Chain Directory | /company-management | Add Partner Drawer | Due Diligence Doc Upload | File Uploader | Accepts ISO/GOTS/OEKO-TEX compliance certificates (PDF/PNG) | Uploads to R2 storage, shows progress bar | Super Admin, Org Admin, Member
Supply Chain Directory | /company-management | Add Partner Drawer | Save Partner Button | Primary Button | Submits partner data to /api/companies endpoint | Success toast -> Card added to directory | Super Admin, Org Admin, Member
Product Master Catalog | /product-management | Catalog Gallery | Product Cards Grid | Card Grid | Visual cards showing product photo, SKU, Category, and spec badges | Hover elevation, click opens spec modal | All Authenticated
Product Master Catalog | /product-management | Header Controls | + New Product SKU Button | Primary Button | Opens Create Product Modal with dynamic category schemas | Opens Create SKU modal | Super Admin, Org Admin, Member
Product Master Catalog | /product-management | Header Controls | Bulk Import CSV Button | Secondary Button | Allows uploading 500+ SKUs via pre-formatted Excel/CSV | Validates schema, displays error summary | Super Admin, Org Admin, Member
Product Master Catalog | /product-management | Product Modal | Category Selector (Textile/Battery/Tech) | Dropdown Select | Switches the dynamic attribute fields accordingly | Form fields refresh dynamically | Super Admin, Org Admin, Member
Product Master Catalog | /product-management | Product Modal | Image Uploader | Image Dropzone | Uploads high-resolution product photography for passports | Generates thumbnail preview | Super Admin, Org Admin, Member
DPP Creation Wizard | /dpp-wizard | Stepper Navigation | 5-Step Stepper Header | Stepper Indicator | Shows current step: 1. Identity, 2. Materials, 3. Performance, 4. Circularity, 5. Review | Active step highlighted, completed steps checkmarked | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 1 | /dpp-wizard?step=1 | Product Identity | Product SKU Autocomplete | Searchable Dropdown | Pulls existing product from Catalog or creates inline | Auto-populates mass, dimensions, category | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 1 | /dpp-wizard?step=1 | Product Identity | Serial Number & GTIN Inputs | Text Inputs | Unique physical identifier for GS1 Digital Link encoding | Validates GS1 GTIN-13/14 checksum | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 2 | /dpp-wizard?step=2 | Materials & Carbon | Dynamic Composition Builder | Dynamic Key-Value Table | Adds materials & % (e.g. 80% Organic Cotton, 20% Poly OR NMC 811 Lithium) | Live calculates total to 100% | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 2 | /dpp-wizard?step=2 | Materials & Carbon | Carbon Footprint Calculator Input | Numeric Input | Total kg CO2e / unit with lifecycle boundary selector (Cradle-to-Gate) | Displays GHG Protocol alignment badge | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 3 | /dpp-wizard?step=3 | Durability & Performance | Repairability Index / Lifetime Slider | Slider & Score input | Score (1-10) or Expected cycle lifetime / years of operation | Visual color rating bar | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 4 | /dpp-wizard?step=4 | Circularity & EoL | Disassembly / Care Manual Uploader | PDF Uploader | Uploads official safe dismantling or garment care guidelines | PDF preview badge with file size | Super Admin, Org Admin, Member, Compliance
DPP Wizard Step 5 | /dpp-wizard?step=5 | 3-Tier Review & Publish | Public / Pro / Authority Visibility Toggles | Switch Toggles | Configures which data attributes are visible to consumers vs repairers vs EU authorities | Real-time 3-tier privacy preview | Super Admin, Org Admin, Compliance
DPP Wizard Step 5 | /dpp-wizard?step=5 | 3-Tier Review & Publish | Publish Passport Button | Primary Button | Locks version, generates immutable audit hash, creates QR code | Confetti animation -> Directs to QR Download | Super Admin, Org Admin, Compliance
Dynamic QR Landing Page | /p/:id (Public) | Header Banner | Product Photo & Eco-Rating | Hero Display | Mobile-first clean header with verified EU DPP seal and brand logo | Fast loading (<150ms) on mobile phones | Public / Anyone
Dynamic QR Landing Page | /p/:id (Public) | Access Tabs | Public / Professional / Authority Tabs | Tab Switcher | Switches between consumer view and role-protected technical portals | Professional/Authority tabs prompt login modal | Public / Anyone
Dynamic QR Landing Page | /p/:id (Public) | Circularity Section | Recycle Drop-Off Bin Finder | Interactive Map / List | Locates nearest certified textile or battery recycling center | Opens GPS directions on mobile | Public / Anyone
GS1 QR Code Manager | /qr-manager | QR Customizer | Format Selector (Vector SVG / High-Res PNG) | Radio Selector | Chooses format optimized for industrial laser etching or garment tags | Updates export preview canvas | Super Admin, Org Admin, Member, Compliance
GS1 QR Code Manager | /qr-manager | QR Customizer | Download QR Button | Primary Button | Instantly downloads production-ready QR asset file | Browser file download triggers | Super Admin, Org Admin, Member, Compliance

## 3. Feature Prioritization
Feature ID | Feature Name | Module / Pillar | MoSCoW Priority | Target Phase | Business & Regulatory Value | Dev Complexity | Owner / Lead
FEAT-001 | Dual-Token JWT & RBAC Auth | Auth & Security | MUST HAVE | Phase 1 (Week 1) | Enterprise security & tenant isolation | Medium | Raman Thakur
FEAT-002 | User Management & Org Switcher | Users & Orgs | MUST HAVE | Phase 1 (Week 1) | Super admin and tenant governance | Medium | Raman Thakur
FEAT-003 | Executive Operations Hub UI | Operations Hub | MUST HAVE | Phase 1 (Week 2) | Executive visibility & compliance score | Low-Medium | Rakshambika & Raman
FEAT-004 | Universal Product Master Catalog | Product Master | MUST HAVE | Phase 1 (Week 2) | SKU repository & dynamic attributes | Medium | Raman Thakur
FEAT-005 | Supply Chain Directory ("To & From") | Supply Chain | MUST HAVE | Phase 1 (Week 3) | Provenance mapping & partner registry | Medium | Rakshambika & Raman
FEAT-006 | 5-Step Dynamic DPP Wizard | DPP Engine | MUST HAVE | Phase 1 (Week 3) | Guided multi-sector passport creation | High | Raman Thakur
FEAT-007 | 3-Tier Data Architecture (Public/Pro/Gov) | Security & DPP | MUST HAVE | Phase 1 (Week 4) | EU ESPR legal access separation | High | Raman Thakur
FEAT-008 | GS1 Digital Link QR Generator | QR & Interop | MUST HAVE | Phase 1 (Week 4) | Standard GS1 URI QR creation & vector export | Medium | Rakshambika & Raman
FEAT-009 | Mobile-Optimized Dynamic QR Viewer | Public Scanner | MUST HAVE | Phase 1 (Week 5) | Instant consumer & repairer scan landing page | Medium | Rakshambika & Raman
FEAT-010 | 10-Year Immutable Audit Trail | Audit Vault | MUST HAVE | Phase 1 (Week 5) | Regulatory inspection persistence | Medium | Raman Thakur
FEAT-011 | JSON-LD & PDF Certificate Export | Export & Interop | SHOULD HAVE | Phase 1 (Week 6) | Customs clearance & standard interop | Medium | Raman Thakur
FEAT-012 | Bulk 500+ SKU CSV/Excel Upload | Product Master | SHOULD HAVE | Phase 2 (Post-Demo) | Enterprise onboarding speed | High | Raman Thakur
FEAT-013 | Supplier Magic Link Portal | Supply Chain | SHOULD HAVE | Phase 2 | Decentralized tier-2 material submission | High | Rakshambika & Raman
FEAT-014 | EU Central Registry API Sync | EU Gateway | COULD HAVE | Phase 2 | Direct sync with Brussels central repository | High | Raman Thakur
FEAT-015 | AI Datasheet / Lab PDF Extractor | AI Automation | COULD HAVE | Phase 3 | Automated test report parsing | Very High | AI/ML Team
FEAT-016 | Blockchain Proof-of-Existence Anchoring | DLT Notarization | WONT HAVE (Now) | Phase 3 | Decentralized dispute proof (optional) | High | Future Roadmap

## 4. 6-Week Project Plan
Week # | Timeline Dates | Workstream & Milestone | Detailed Tasks & Deliverables | Dependencies | Primary Owner | Demo-Ready Milestone Status
Week 1 | Oct 08 – Oct 14, 2026 | Documentation & UI Mockup Sign-off | Finalize Excel Blueprint, User Journeys, 4-5 Figma Design Mockups, Graphic Language Rules. Present in Tuesday Meeting. | Stakeholder Feedback | Rakshambika & Raman | Planning Gate Approved
Week 2 | Oct 15 – Oct 21, 2026 | Core Foundation & Universal Catalog | Finalize Auth + User RBAC, build Universal Product Master Catalog with dynamic schemas (Textile, Battery, Tech). | Figma Mockups Approved | Raman Thakur | Internal Milestone
Week 3 | Oct 22 – Oct 28, 2026 | Company Directory & 5-Step Wizard | Implement Supply Chain "To & From" Directory, construct 5-Step Dynamic DPP Wizard frontend + backend persistence. | Product Catalog APIs | Rakshambika & Raman | Internal Milestone
Week 4 | Oct 29 – Nov 04, 2026 | 3-Tier Security & GS1 QR Engine | Implement 3-Tier data access separation (Public/Pro/Gov), GS1 Digital Link URL resolver, Vector SVG/PNG QR Generator. | DPP Wizard Data Model | Raman Thakur | Round 1 Testing (2 Testers)
Week 5 | Nov 05 – Nov 11, 2026 | Mobile Scan Viewer & Audit Trail | Build Mobile-first QR Landing Page (/p/:id), 10-year immutable audit trail logging, JSON-LD / PDF export pipeline. | QR Engine & 3-Tier Filter | Rakshambika & Raman | Round 2 Testing (4 Testers)
Week 6 | Nov 12 – Nov 18, 2026 | Hardening, E2E Polish & Final Demo | Fix test findings, refine light/dark UI contrast, verify cross-browser performance, final end-to-end rehearsal. | Round 2 Feedback | Rakshambika & Raman | 🎉 DEMO-READY (Nov 18, 2026)

## 5. Staggered Testing Strategy
Testing Round | Target Date | Group Size | Nominated Testers & Roles | Scope & User Journeys Tested | Unbiased Testing Protocol & Rules | Success Criteria / Exit Gate
Round 1 (Alpha) | Nov 02 – Nov 04, 2026 | 2 Testers | Tester 1: Internal QA / Dev Lead Tester 2: Product Specialist | Smoke testing: User login, Product SKU creation, DPP Wizard 5-step form entry, QR Code generation. | Strict isolation: Testers receive only user credentials and a task goal (e.g. "Create a passport for a Garment SKU"). No prior demo shown. | Zero blocker bugs, 100% form completion rate
Round 2 (Beta) | Nov 09 – Nov 11, 2026 | 4 Testers | Tester 3: Compliance Lead Tester 4: Supply Chain Specialist Tester 5: UI/UX Expert Tester 6: Non-technical Team Member | End-to-End Journey: Partner creation -> SKU Catalog -> 3-Tier Access Configuration -> Mobile QR Scan -> Audit Log Verification. | Blind usability test: Testers record screen while performing realistic tasks. UI/UX confusion points logged numerically without prompting. | SUS (System Usability Score) > 80/100, zero security leak between tiers
Round 3 (Pre-Demo) | Nov 14 – Nov 16, 2026 | 6 Testers | Tester 7: Executive Stakeholder Tester 8: External Pilot Client Tester 9: Senior Architect Tester 10-12: Cross-functional Members | Full Multi-Industry Workflows (Textiles & Batteries), bulk data handling, mobile responsiveness, PDF/JSON-LD export validation. | Final acceptance test: Evaluates visual polish, alignment with Monkspaces brand guidelines, load speed under simulated network. | Formal sign-off by all 6 testers for Live Stakeholder Demo

## 6. UI-UX & Graphic Rules
Design Category | Design Standard / Token | Specification & Value | Implementation Rule / Rationale
Typography | Primary Headings & Body | Inter / Plus Jakarta Sans / Segoe UI | Clean, modern sans-serif typography matching Monkspaces corporate web standards.
Typography | Data & Serial Numbers | JetBrains Mono / Roboto Mono | Monospace font used strictly for GTIN, Serial Numbers, Hashes, and QR link strings.
Color Palette | Primary Brand Color | Emerald / Deep Teal (#0F766E, #059669) | Represents sustainability, eco-design, and European Green Deal trust.
Color Palette | Slate Neutral Scale | Slate 50 (#F8FAFC) to Slate 900 (#0F172A) | High-contrast neutral backgrounds, crisp border lines (#E2E8F0), no harsh pure black (#000000).
Color Palette | Status Indicators | Published: #10B981 ¦ Review: #F59E0B ¦ Draft: #64748B ¦ Error: #EF4444 | Consistent WCAG AAA contrast for all regulatory status badges.
Iconography | Icon System | Lucide Icons / Heroicons (2px Outline) | Mili Jain Directive: Strictly avoid cartoonish icons. Use single-source flat line drawings.
Theme Architecture | Default Theme Mode | Light Mode (Default) + Dark Mode (Toggle) | Default clean Light Mode matching web portal, with optional Dark Mode for battery energy savings.
Components & Layout | Spacing & Elevation | 8pt Grid System (p-2, p-4, p-6), subtle shadow-sm/shadow-md | Clean structural alignment with soft border radius (rounded-lg: 8px to 12px).
Design Options | Figma Mockup Sets | 4-5 Distinct Layout Variations | To be presented in Tuesday meeting: 1. Clean Enterprise, 2. Modern Card-Grid, 3. Compact Dense Table, 4. Interactive Flow.